PROGRAMME DEVELOPMENT PLAN

| ACTIVITY | Oct 12 | Nov 12 | Dec 12 | Jan 13 | Feb 13 | Mar 13 | Apr 13 | May 13 | June 13 | July 13 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Development of the Prospectus | 23-29 |  |  |  |  |  |  |  |  |  |
| Meeting of the Prospectus Development Group (PDG) | 29 |  |  |  |  |  |  |  |  |  |
| PDG conducts further consultation with young people through various focus groups organised by partners and voluntary organisations | 29 | 05 |  |  |  |  |  |  |  |  |
| Prospectus submitted |  | 05 |  |  |  |  |  |  |  |  |
| Due diligence process for potential delivery partners |  |  | 01 |  |  |  |  |  |  |  |
| Creating a final list of delivery partners who passed due diligence (framework) |  |  | 15 |  |  |  |  |  |  |  |
| Development of commissioning framework and documentation |  |  |  | 15 |  |  |  |  |  |  |
| Appointment of the Programme board (Prince 2) |  |  |  | 15 |  |  |  |  |  |  |
| Appointment of the Commissioning Panel |  |  |  | 30 |  |  |  |  |  |  |
| Approval of the Prospectus by BLF |  |  |  |  | 15 |  |  |  |  |  |
| Business Planning Commenced |  |  |  |  | 15 |  |  |  |  |  |
| Commissioning process completed |  |  |  |  |  | 15 |  |  |  |  |
| Delivery partners selected and SLAs drafted (not issued) |  |  |  |  |  |  | 01 |  |  |  |
| Partnership Agreement drafted |  |  |  |  |  |  | 15 |  |  |  |
| Business plan for year 1and 2 agreed by the Programme Board and submitted alongside a draft Partnership Agreement |  |  |  |  |  |  |  | 01 |  |  |
| Programme Plans approved by BLF |  |  |  |  |  |  |  |  | 01 |  |
| SLAs signed and issued |  |  |  |  |  |  |  |  | 15 |  |
| Delivery of the project commences |  |  |  |  |  |  |  |  |  | 01 |

Partner Selection and Board st up

November - January 2013

Bussines Planning and Commissioning

January 2013

May 2013

- Business plan for year 1and 2 agreed by the Programme Board and submitted

- Delivery partners selected and SLAs drafted (not issued)

June 2013

- Project Plans approved by BLF

- SLAs signed and issued

- Delivery of the project commences